## 00_README
KDL SEO PLAN · kingdomlandkids.com redesign
Generated 2026-09-11 · SentryX / Doris Le · Sheets are bilingual VN · EN
Sheet / Mục | Tiếng Việt | English
Mục đích · Purpose | Kế hoạch SEO đi kèm bản redesign kingdomlandkids.com (3D hero · UI/UX · SEO). Mỗi sheet là một lớp việc: từ khóa → meta từng trang → kỹ thuật → schema → nội dung → backlink → redirect → câu hỏi mở. | SEO plan shipped with the kingdomlandkids.com redesign. Each sheet is one layer: keywords → per-page meta → technical → schema → content → links → redirects → open questions.
01_Keyword_Map | Cụm từ khóa theo funnel, intent và trang đích. Volume/KD điền từ GSC + Ahrefs/Semrush sau khi có access — cột Priority là đánh giá định tính. | Keyword clusters by funnel stage, intent and target page. Fill volume/KD from GSC + Ahrefs/Semrush once access exists — Priority is a qualitative call.
02_Page_Meta | Đọc trực tiếp từ dist/ sau khi build: title, meta description, H1, canonical, số ký tự, schema. Đây là 'nguồn sự thật' để QA. | Read straight from the built dist/: title, description, H1, canonical, character counts, schema. Use as the QA source of truth.
03_Technical | Checklist kỹ thuật: cái gì đã có trong build, cái gì phải làm lúc launch (DNS, GSC, analytics, redirect). | Technical checklist: what the build already does vs. what must happen at launch (DNS, GSC, analytics, redirects).
04_Schema_Map | Loại structured data trên từng trang và cách kiểm tra. | Structured-data types per page and how to validate.
05_Content_Calendar | 12 tuần blog (Sep 14 → Dec 6, 2026) bám mùa: back-to-school, Thanksgiving, Advent/Christmas, chuẩn bị MLK Day & Black History Month. | 12-week blog calendar (Sep 14 → Dec 6, 2026) following the season: back-to-school, Thanksgiving, Advent/Christmas, MLK Day & Black History Month prep.
06_Links_Distribution | Nơi kiếm backlink/đề cập chất lượng: roundup blogs Christian mom, directory faith apps, church partners, YouTube/IG bio. | Where quality links/mentions come from: Christian-mom roundup blogs, faith-app directories, church partners, YouTube/IG bios.
07_Redirect_Map | Khung map URL cũ → mới. Cần crawl site hiện tại (Screaming Frog) để điền cột URL cũ. | Old → new URL map. Crawl the current site (Screaming Frog) to fill the old-URL column.
08_Open_Questions | Những gì cần Doris/Nick xác nhận trước khi go-live. | What Doris/Nick must confirm before go-live.
Cách dùng · How to use | 1) Duyệt 08 trước → chốt giá, tuổi, URL. 2) Dev chạy 03 lúc launch. 3) Content team chạy 05 hàng tuần. 4) Sau 4 tuần: đối chiếu GSC với 01 và cập nhật Priority. | 1) Clear sheet 08 first → lock pricing, ages, URLs. 2) Dev runs 03 at launch. 3) Content runs 05 weekly. 4) After 4 weeks: compare GSC with 01 and re-rank Priority.

## 01_Keyword_Map
Keyword map · Bản đồ từ khóa
Priority: P0 = ship & measure now · P1 = next 90 days · P2 = opportunistic. Fill Volume / KD from GSC + Ahrefs once access exists.
Cluster / Cụm | Keyword / Từ khóa | Intent / Ý định | Funnel | Priority | Target page / Trang đích | Notes / Ghi chú | Volume (fill) | KD (fill)
Brand | kingdomland kids | Navigational | Bottom | P0 | / , go.kingdomlandkids.com | Own every brand variant; add 'Kingdomland Kids' to every title tag suffix (done).
Brand | kingdom land kids | Navigational | Bottom | P0 | / , go.kingdomlandkids.com | Own every brand variant; add 'Kingdomland Kids' to every title tag suffix (done).
Brand | kingdomland kids app | Navigational | Bottom | P0 | / , go.kingdomlandkids.com | Own every brand variant; add 'Kingdomland Kids' to every title tag suffix (done).
Brand | kingdomland kids login | Navigational | Bottom | P0 | / , go.kingdomlandkids.com | Own every brand variant; add 'Kingdomland Kids' to every title tag suffix (done).
Brand | kingdomland kids free | Navigational | Bottom | P0 | / , go.kingdomlandkids.com | Own every brand variant; add 'Kingdomland Kids' to every title tag suffix (done).
Brand | kingdomland kids marvelous light | Navigational | Bottom | P0 | / , go.kingdomlandkids.com | Own every brand variant; add 'Kingdomland Kids' to every title tag suffix (done).
Brand | kingdomland kids youtube | Navigational | Bottom | P0 | / , go.kingdomlandkids.com | Own every brand variant; add 'Kingdomland Kids' to every title tag suffix (done).
Category | christian streaming for kids | Commercial | Middle | P0 | / | Home H1 kicker + description target this cluster.
Category | christian streaming service for kids | Commercial | Middle | P0 | / | Home H1 kicker + description target this cluster.
Category | christian kids streaming app | Commercial | Middle | P0 | / | Home H1 kicker + description target this cluster.
Category | faith based streaming for kids | Commercial | Middle | P0 | / | Home H1 kicker + description target this cluster.
Category | christian netflix for kids | Commercial | Middle | P0 | / | Home H1 kicker + description target this cluster.
Category | christian alternative to youtube kids | Commercial | Middle | P0 | / | Home H1 kicker + description target this cluster.
Category | ad free kids streaming christian | Commercial | Middle | P0 | / | Home H1 kicker + description target this cluster.
Shows | christian shows for kids | Commercial / Informational | Middle | P0 | /shows/ , blog checklist | Shows index + '6-point checklist' article. Add a '10 best…' roundup only if we are comfortable naming others.
Shows | christian cartoons for kids | Commercial / Informational | Middle | P0 | /shows/ , blog checklist | Shows index + '6-point checklist' article. Add a '10 best…' roundup only if we are comfortable naming others.
Shows | bible cartoons for kids | Commercial / Informational | Middle | P0 | /shows/ , blog checklist | Shows index + '6-point checklist' article. Add a '10 best…' roundup only if we are comfortable naming others.
Shows | christian tv shows for toddlers | Commercial / Informational | Middle | P0 | /shows/ , blog checklist | Shows index + '6-point checklist' article. Add a '10 best…' roundup only if we are comfortable naming others.
Shows | christian shows for preschoolers | Commercial / Informational | Middle | P0 | /shows/ , blog checklist | Shows index + '6-point checklist' article. Add a '10 best…' roundup only if we are comfortable naming others.
Shows | animated bible stories for kids | Commercial / Informational | Middle | P0 | /shows/ , blog checklist | Shows index + '6-point checklist' article. Add a '10 best…' roundup only if we are comfortable naming others.
Shows | bible stories for kids videos | Commercial / Informational | Middle | P0 | /shows/ , blog checklist | Shows index + '6-point checklist' article. Add a '10 best…' roundup only if we are comfortable naming others.
Marvelous Light | marvelous light kids show | Navigational / Informational | Middle | P1 | /shows/marvelous-light/ | Long-tail is low volume but converts; TVSeries schema in place.
Marvelous Light | marvelous light lucy and leo | Navigational / Informational | Middle | P1 | /shows/marvelous-light/ | Long-tail is low volume but converts; TVSeries schema in place.
Marvelous Light | fruits of the spirit cartoon | Navigational / Informational | Middle | P1 | /shows/marvelous-light/ | Long-tail is low volume but converts; TVSeries schema in place.
Marvelous Light | bible cartoon talking animals | Navigational / Informational | Middle | P1 | /shows/marvelous-light/ | Long-tail is low volume but converts; TVSeries schema in place.
Worship & verses | kids worship songs | Informational | Top | P1 | /shows/worship-and-memory-verses/ | Consider a free sampler playlist on YouTube linking back.
Worship & verses | bible memory verse songs for kids | Informational | Top | P1 | /shows/worship-and-memory-verses/ | Consider a free sampler playlist on YouTube linking back.
Worship & verses | scripture songs for kids | Informational | Top | P1 | /shows/worship-and-memory-verses/ | Consider a free sampler playlist on YouTube linking back.
Worship & verses | memory verse songs preschool | Informational | Top | P1 | /shows/worship-and-memory-verses/ | Consider a free sampler playlist on YouTube linking back.
Worship & verses | christian songs for toddlers | Informational | Top | P1 | /shows/worship-and-memory-verses/ | Consider a free sampler playlist on YouTube linking back.
Fruits of the Spirit | fruits of the spirit for kids | Informational | Top | P1 | /blog/fruits-of-the-spirit-for-kids/ → /shows/fruits-of-virtue/ | Evergreen; Sunday-school teachers search this year-round.
Fruits of the Spirit | fruit of the spirit lesson for kids | Informational | Top | P1 | /blog/fruits-of-the-spirit-for-kids/ → /shows/fruits-of-virtue/ | Evergreen; Sunday-school teachers search this year-round.
Fruits of the Spirit | fruits of the spirit explained for children | Informational | Top | P1 | /blog/fruits-of-the-spirit-for-kids/ → /shows/fruits-of-virtue/ | Evergreen; Sunday-school teachers search this year-round.
Fruits of the Spirit | galatians 5:22 for kids | Informational | Top | P1 | /blog/fruits-of-the-spirit-for-kids/ → /shows/fruits-of-virtue/ | Evergreen; Sunday-school teachers search this year-round.
Family devotional | family devotional for preschoolers | Informational | Top | P1 | /blog/five-minute-family-devotional/ | Highest-intent parent pain point in the Q3 plan ('faith-filled screen time').
Family devotional | 5 minute family devotional | Informational | Top | P1 | /blog/five-minute-family-devotional/ | Highest-intent parent pain point in the Q3 plan ('faith-filled screen time').
Family devotional | how to do family devotions with toddlers | Informational | Top | P1 | /blog/five-minute-family-devotional/ | Highest-intent parent pain point in the Q3 plan ('faith-filled screen time').
Family devotional | family bible time with young kids | Informational | Top | P1 | /blog/five-minute-family-devotional/ | Highest-intent parent pain point in the Q3 plan ('faith-filled screen time').
Family devotional | bedtime bible routine kids | Informational | Top | P1 | /blog/five-minute-family-devotional/ | Highest-intent parent pain point in the Q3 plan ('faith-filled screen time').
Black History Beats | black history songs for kids | Informational / Seasonal | Top | P1 | /shows/black-history-beats/ | Seasonal peaks: Jan (MLK), Feb (BHM), Jun (Juneteenth). Publish 6 weeks ahead.
Black History Beats | jackie robinson song for kids | Informational / Seasonal | Top | P1 | /shows/black-history-beats/ | Seasonal peaks: Jan (MLK), Feb (BHM), Jun (Juneteenth). Publish 6 weeks ahead.
Black History Beats | bessie coleman for kids | Informational / Seasonal | Top | P1 | /shows/black-history-beats/ | Seasonal peaks: Jan (MLK), Feb (BHM), Jun (Juneteenth). Publish 6 weeks ahead.
Black History Beats | mlk songs for kids | Informational / Seasonal | Top | P1 | /shows/black-history-beats/ | Seasonal peaks: Jan (MLK), Feb (BHM), Jun (Juneteenth). Publish 6 weeks ahead.
Black History Beats | black history month videos for kids christian | Informational / Seasonal | Top | P1 | /shows/black-history-beats/ | Seasonal peaks: Jan (MLK), Feb (BHM), Jun (Juneteenth). Publish 6 weeks ahead.
Black History Beats | juneteenth videos for kids | Informational / Seasonal | Top | P1 | /shows/black-history-beats/ | Seasonal peaks: Jan (MLK), Feb (BHM), Jun (Juneteenth). Publish 6 weeks ahead.
Audience-specific | christian shows for black kids | Commercial | Middle | P0 | / , /about/ | Under-served, low competition, exact brand fit. About page carries this story.
Audience-specific | bible cartoons black characters | Commercial | Middle | P0 | / , /about/ | Under-served, low competition, exact brand fit. About page carries this story.
Audience-specific | african american christian kids videos | Commercial | Middle | P0 | / , /about/ | Under-served, low competition, exact brand fit. About page carries this story.
Audience-specific | black christian family streaming | Commercial | Middle | P0 | / , /about/ | Under-served, low competition, exact brand fit. About page carries this story.
Church | children's ministry videos | Commercial (B2B) | Middle | P1 | /churches/ | Pair with outreach to children's pastors; partner codes already in the model.
Church | sunday school videos for kids | Commercial (B2B) | Middle | P1 | /churches/ | Pair with outreach to children's pastors; partner codes already in the model.
Church | kids church videos free | Commercial (B2B) | Middle | P1 | /churches/ | Pair with outreach to children's pastors; partner codes already in the model.
Church | children's church curriculum videos | Commercial (B2B) | Middle | P1 | /churches/ | Pair with outreach to children's pastors; partner codes already in the model.
Church | church streaming for kids families | Commercial (B2B) | Middle | P1 | /churches/ | Pair with outreach to children's pastors; partner codes already in the model.
Comparison | minno vs yippee | Commercial | Middle | P2 | future blog | Only with verified facts about competitors — the May plan dropped unverified competitor pricing. Keep to features, not prices.
Comparison | yippee tv alternative | Commercial | Middle | P2 | future blog | Only with verified facts about competitors — the May plan dropped unverified competitor pricing. Keep to features, not prices.
Comparison | minno alternative | Commercial | Middle | P2 | future blog | Only with verified facts about competitors — the May plan dropped unverified competitor pricing. Keep to features, not prices.
Comparison | best christian streaming service for kids 2026 | Commercial | Middle | P2 | future blog | Only with verified facts about competitors — the May plan dropped unverified competitor pricing. Keep to features, not prices.
Comparison | pure flix kids alternative | Commercial | Middle | P2 | future blog | Only with verified facts about competitors — the May plan dropped unverified competitor pricing. Keep to features, not prices.
Preschool | christian abc videos | Informational | Top | P2 | /shows/abcs-and-numbers/ | Broad and competitive; win on 'safe/no ads' angle.
Preschool | christian counting songs toddlers | Informational | Top | P2 | /shows/abcs-and-numbers/ | Broad and competitive; win on 'safe/no ads' angle.
Preschool | safe preschool videos no ads | Informational | Top | P2 | /shows/abcs-and-numbers/ | Broad and competitive; win on 'safe/no ads' angle.
Preschool | christian preschool learning videos | Informational | Top | P2 | /shows/abcs-and-numbers/ | Broad and competitive; win on 'safe/no ads' angle.

## 02_Page_Meta
Per-page meta · Meta từng trang (đọc từ dist/)
Google shows ~60 chars of a title and ~155–160 of a description; longer is not an error, it just gets truncated. Series titles run long on purpose (brand suffix) — trim if CTR is weak.
URL | Title tag | Title chars | Meta description | Desc chars | H1 | H2 count | Words (approx) | Canonical | Robots | JSON-LD types | QA
/ | Kingdomland Kids — Christian Streaming for Kids ¦ Bible Stories, Worship & Quiz Games | 85 | Ad-free Christian streaming for kids ages 2–10. Animated Bible stories like Marvelous Light, worship songs, memory verse tracks, life-skills shows and family quiz games. Try it free — no card needed. | 199 | Christian streaming for kids · ages 2–10 Biblical adventures for young hearts | 7 | 1244 | https://kingdomlandkids.com/ | index,follow,max-image-preview:large | Organization, WebSite, WebApplication/SoftwareApplication | title 85 chars (>60); description 199 chars (>160)
/404.html | Page not found ¦ Kingdomland Kids | 33 | This path leads off the map. Head back to Kingdomland Kids. | 59 | This path leads off the map | 0 | 150 | https://kingdomlandkids.com/404.html | noindex,follow | Organization, WebSite | OK
/about/ | About Kingdomland Kids — Made by Families Who Wanted Better for Their Kids | 74 | Kingdomland Kids grew from a YouTube channel loved by 159K+ families into an ad-free Christian streaming app for kids. Our story, what we believe, and why representation matters in Bible stories for children. | 208 | Made by families who wanted better for their kids | 3 | 495 | https://kingdomlandkids.com/about/ | index,follow,max-image-preview:large | Organization, WebSite, AboutPage, BreadcrumbList | title 74 chars (>60); description 208 chars (>160)
/blog/ | The Kingdomland Blog — Faith at Home for Busy Parents | 53 | Short, practical reads for Christian parents: family devotionals that fit real schedules, the fruits of the Spirit explained for kids, and how to choose Christian shows for children. | 182 | Faith at home, for parents with 5 minutes | 1 | 281 | https://kingdomlandkids.com/blog/ | index,follow,max-image-preview:large | Organization, WebSite, BreadcrumbList | description 182 chars (>160)
/churches/ | Kingdomland Kids for Churches, Children's Ministries & Christian Schools | 72 | Bring Kingdomland Kids to your congregation: partner rates and promo codes for your families, ready-made children's ministry videos with discussion prompts, and a launch kit. Email hello@kingdomlandkids.com to start. | 216 | Kingdomland Kids for churches, ministries & schools | 2 | 438 | https://kingdomlandkids.com/churches/ | index,follow,max-image-preview:large | Organization, WebSite, BreadcrumbList | title 72 chars (>60); description 216 chars (>160)
/contact/ | Contact Kingdomland Kids — Support, Churches & Press | 52 | Contact Kingdomland Kids: support for families, church and ministry partnerships, press and creator enquiries. Email hello@kingdomlandkids.com — a real person replies. | 167 | We read every message | 0 | 242 | https://kingdomlandkids.com/contact/ | index,follow,max-image-preview:large | Organization, WebSite, ContactPage, BreadcrumbList | description 167 chars (>160)
/faq/ | FAQ — Ages, Devices, Free Plan, Cancelling & More ¦ Kingdomland Kids | 68 | Answers to common questions about Kingdomland Kids: what ages it's for, which devices work, how the free plan works, cancelling, the free storybook, church pricing and whether there are ads. | 190 | Questions parents ask | 1 | 536 | https://kingdomlandkids.com/faq/ | index,follow,max-image-preview:large | Organization, WebSite, FAQPage, BreadcrumbList | title 68 chars (>60); description 190 chars (>160)
/pricing/ | Pricing — Free, Monthly $9.99 or Annual $69.99 ¦ Kingdomland Kids | 65 | Kingdomland Kids pricing: try free with no card (60-second previews), Monthly $9.99 with 20% off your first month, or Annual $69.99 ($5.83/mo, save 42%) with a free Marvelous Light storybook shipped. Cancel anytime. | 215 | Pricing that's fair to families | 3 | 718 | https://kingdomlandkids.com/pricing/ | index,follow,max-image-preview:large | Organization, WebSite, WebApplication/SoftwareApplication, BreadcrumbList | title 65 chars (>60); description 215 chars (>160)
/privacy/ | Privacy Policy ¦ Kingdomland Kids | 33 | How Kingdomland Kids collects, uses and protects your family's information. | 75 | Privacy Policy | 0 | 229 | https://kingdomlandkids.com/privacy/ | noindex,follow | Organization, WebSite | OK
/shows/ | Christian Shows for Kids — Every Series on Kingdomland Kids | 59 | Browse every Christian show for kids on Kingdomland Kids: Marvelous Light Bible stories, Black History Beats, Bible Fruits of Virtue, Little Agent life skills, ABCs & Numbers, worship and memory verse playlists. Ad-free, ages 2–10. | 231 | Every show on Kingdomland Kids | 2 | 559 | https://kingdomlandkids.com/shows/ | index,follow,max-image-preview:large | Organization, WebSite, BreadcrumbList | description 231 chars (>160)
/terms/ | Terms of Service ¦ Kingdomland Kids | 35 | The terms that govern your Kingdomland Kids subscription. | 57 | Terms of Service | 0 | 222 | https://kingdomlandkids.com/terms/ | noindex,follow | Organization, WebSite | OK
/blog/christian-shows-for-kids-checklist/ | What to Look for in a Christian Show for Kids: a 6-Point Checklist ¦ Kingdomland Kids | 85 | Choosing Christian shows for kids? Six questions to ask before you press play: Bible accuracy, ads and autoplay, representation, pacing for young attention spans, what happens after the episode, and cost. | 204 | What to look for in a Christian show for kids: a 6-point checklist | 8 | 611 | https://kingdomlandkids.com/blog/christian-shows-for-kids-checklist/ | index,follow,max-image-preview:large | Organization, WebSite, Article, BreadcrumbList | title 85 chars (>60); description 204 chars (>160)
/blog/five-minute-family-devotional/ | How to Start a 5-Minute Family Devotional With a 4-Year-Old ¦ Kingdomland Kids | 78 | A realistic family devotional routine for preschoolers: one verse, one question, one song, five minutes. What to do when they wiggle, and how memory verse tracks make Scripture stick. | 183 | How to start a 5-minute family devotional with a 4-year-old | 5 | 592 | https://kingdomlandkids.com/blog/five-minute-family-devotional/ | index,follow,max-image-preview:large | Organization, WebSite, Article, BreadcrumbList | title 78 chars (>60); description 183 chars (>160)
/blog/fruits-of-the-spirit-for-kids/ | The Fruits of the Spirit for Kids: A Parent's Plain-English Guide ¦ Kingdomland Kids | 84 | All nine fruits of the Spirit from Galatians 5:22–23 explained in words a six-year-old understands, with one thing to try for each — plus a memory trick and shows that teach them. | 179 | The fruits of the Spirit for kids: a parent's plain-English guide | 5 | 610 | https://kingdomlandkids.com/blog/fruits-of-the-spirit-for-kids/ | index,follow,max-image-preview:large | Organization, WebSite, Article, BreadcrumbList | title 84 chars (>60); description 179 chars (>160)
/shows/abcs-and-numbers/ | ABCs & Numbers — Early learning with a joyful heart ¦ Kingdomland Kids | 70 | ABCs & Numbers on Kingdomland Kids: gentle early-learning videos for toddlers and preschoolers ages 2–5 — letters, numbers, colors and songs, ad-free and safe. | 159 | ABCs & Numbers | 5 | 420 | https://kingdomlandkids.com/shows/abcs-and-numbers/ | index,follow,max-image-preview:large | Organization, WebSite, TVSeries, BreadcrumbList | title 70 chars (>60)
/shows/bible-adventures/ | Bible Adventures — Big stories, explained for curious kids ¦ Kingdomland Kids | 77 | Bible Adventures on Kingdomland Kids explains the big stories of Scripture for kids ages 5–10 — the Exodus, Psalm 23 and more. 15 episodes, ad-free. Try it free, no card needed. | 177 | Bible Adventures | 5 | 437 | https://kingdomlandkids.com/shows/bible-adventures/ | index,follow,max-image-preview:large | Organization, WebSite, TVSeries, BreadcrumbList | title 77 chars (>60); description 177 chars (>160)
/shows/bible-in-clay/ | Bible in Clay — Creation, told in clay ¦ Kingdomland Kids | 57 | Bible in Clay on Kingdomland Kids: claymation Bible stories for kids, starting with Creation. Slow, wonder-filled storytelling for ages 3–8. | 140 | Bible in Clay | 5 | 395 | https://kingdomlandkids.com/shows/bible-in-clay/ | index,follow,max-image-preview:large | Organization, WebSite, TVSeries, BreadcrumbList | OK
/shows/black-history-beats/ | Black History Beats — Turn history into a song ¦ Kingdomland Kids | 65 | Black History Beats on Kingdomland Kids turns Black history into songs for kids — Jackie Robinson, Bessie Coleman and Dr. Martin Luther King Jr. Celebratory, faith-filled music videos for ages 5–10. | 198 | Black History Beats | 5 | 438 | https://kingdomlandkids.com/shows/black-history-beats/ | index,follow,max-image-preview:large | Organization, WebSite, TVSeries, BreadcrumbList | title 65 chars (>60); description 198 chars (>160)
/shows/fruits-of-virtue/ | Bible Fruits of Virtue — One fruit of the Spirit at a time ¦ Kingdomland Kids | 77 | Bible Fruits of Virtue on Kingdomland Kids teaches the fruits of the Spirit to kids ages 4–8 — gentleness, goodness, faithfulness and love — one episode at a time. Ad-free Christian kids videos. | 194 | Bible Fruits of Virtue | 5 | 445 | https://kingdomlandkids.com/shows/fruits-of-virtue/ | index,follow,max-image-preview:large | Organization, WebSite, TVSeries, BreadcrumbList | title 77 chars (>60); description 194 chars (>160)
/shows/little-agent/ | Little Agent — Everyday missions, real-life skills ¦ Kingdomland Kids | 69 | Little Agent on Kingdomland Kids: 8 life-skills episodes where a kid agent takes on everyday missions — honesty, responsibility, kindness. Ages 4–8, ad-free. | 157 | Little Agent | 5 | 409 | https://kingdomlandkids.com/shows/little-agent/ | index,follow,max-image-preview:large | Organization, WebSite, TVSeries, BreadcrumbList | title 69 chars (>60)
/shows/marvelous-light/ | Marvelous Light — Lucy & Leo’s Bible adventures ¦ Kingdomland Kids | 66 | Watch Marvelous Light on Kingdomland Kids: Lucy and Leo discover the fruits of the Spirit in a magical world of talking animals. 24 animated Bible-story episodes for ages 4–8 — Moses, David, Daniel, Jonah, Noah, Creation and more. Try it free. | 243 | Marvelous Light | 5 | 494 | https://kingdomlandkids.com/shows/marvelous-light/ | index,follow,max-image-preview:large | Organization, WebSite, TVSeries, BreadcrumbList | title 66 chars (>60); description 243 chars (>160)
/shows/worship-and-memory-verses/ | Worship & Memory Verses — Songs and Scripture that stay ¦ Kingdomland Kids | 74 | Kids worship songs and Bible memory verse tracks on Kingdomland Kids. Ready-made playlists for family worship, mornings and bedtime. Ad-free Christian music for kids. | 166 | Worship & Memory Verses | 5 | 437 | https://kingdomlandkids.com/shows/worship-and-memory-verses/ | index,follow,max-image-preview:large | Organization, WebSite, TVSeries, BreadcrumbList | title 74 chars (>60); description 166 chars (>160)

## 03_Technical
Technical checklist · Checklist kỹ thuật
Status: Done in build · To do at launch · Later. Owner column is a suggestion.
Area / Nhóm | Item / Hạng mục | Status | Owner | Notes / Ghi chú
Crawl & index | Sitemap.xml auto-generated from the build, lastmod = build date | Done in build | Dev | Submit in Google Search Console + Bing Webmaster after launch.
Crawl & index | robots.txt allows all, blocks /privacy/ & /terms/ placeholders, points to sitemap | Done in build | Dev | Remove the Disallow lines once real legal pages exist.
Crawl & index | Canonical + hreflang (en, x-default) on every page | Done in build | —
Crawl & index | Custom 404.html (noindex) | Done in build | Dev | Netlify/GH Pages pick up 404.html automatically; Vercel/Cloudflare need a rewrite rule.
Crawl & index | 301 redirects from every old URL (see 07_Redirect_Map) | To do at launch | Dev | Crawl current site first. Never launch without this — it protects existing rankings.
Crawl & index | Force https + one host (www → apex or apex → www) + trailing-slash consistency | To do at launch | Dev / DNS | Build uses trailing slashes (/pricing/). Configure the host to redirect /pricing → /pricing/.
Crawl & index | Google Search Console: DNS-verify kingdomlandkids.com (covers go. subdomain too) | To do at launch | Nick / Dev | Also verify go.kingdomlandkids.com as a URL-prefix property to see funnel pages.
Structured data | JSON-LD @graph: Organization, WebSite, WebApplication+Offers, TVSeries, FAQPage, Article, BreadcrumbList, AboutPage, ContactPage | Done in build | — | Validate with https://validator.schema.org and Google Rich Results Test after launch.
Structured data | Organization logo 512×512 PNG, sameAs → YouTube/IG/FB | Done (placeholder logo) | Doris | Swap logo-512.png for the real wordmark-on-navy asset; confirm IG/FB URLs.
On-page | One H1 per page with the primary keyword; kicker keeps SEO phrase inside the H1 on the home page | Done in build | —
On-page | Title ≤ 60 chars where possible; brand suffix on every page; unique meta descriptions | Done (see 02 QA column) | Doris | Series titles intentionally long; trim if GSC shows truncation hurting CTR.
On-page | Internal linking: every show ↔ related shows, blog ↔ shows, pricing ↔ churches, footer hub | Done in build | —
On-page | Image alt / aria on decorative SVG (aria-hidden) and meaningful controls | Done in build | — | When real key art replaces the emblems, give each <img> a descriptive alt (series name + scene).
Performance | Hero is code (WebGL), no LCP image; fonts preconnected with display=swap; single CSS; deferred JS | Done in build | — | Measure with PageSpeed Insights after deploy. Target: LCP < 2.5s mobile, CLS < 0.1, INP < 200ms.
Performance | Three.js only loads on the home page; DPR capped; render pauses off-screen; reduced-motion = static frame | Done in build | — | Vendored (687 KB min, ~170 KB brotli). Served self-hosted, cacheable for a year.
Performance | Enable Brotli/gzip + long cache headers for /assets/ (immutable) on the host | To do at launch | Dev | Netlify/Vercel/Cloudflare do this by default.
Performance | Convert real show thumbnails to AVIF/WebP ≤ 60 KB, 16:10, with width/height attributes | To do (when art arrives) | Doris / Dev | Prevents CLS; keeps mobile LCP fast.
Analytics | GA4 property + Meta Pixel on the site (partials/analytics.html) | To do at launch | Dev | Placeholders only — no fake IDs shipped.
Analytics | App must fire Lead (free signup), Subscribe / StartTrial, Purchase (value, currency) to Meta + GA4 | To do — blocking ads efficiency | Khai / Dev | Sep 7 audit: pixel only sends PageView + AddToCart. Meta cannot optimise for subscribers until this ships.
Analytics | UTM discipline: site CTAs → go.kingdomlandkids.com with utm_source=site&utm_medium=cta&utm_campaign=<page> | Partly done (footer form) | Doris | Add UTMs to every CTA href in site.json if the app can read them.
Security | HSTS, X-Content-Type-Options, Referrer-Policy, CSP (allow fonts.googleapis/gstatic + self) | To do at launch | Dev | Static host header rules.
Accessibility | Skip link, focus-visible styles, aria labels, colour contrast on navy/cream/gold (AA) | Done in build | — | Gold-on-navy small text kept ≥ 700 weight for contrast.
Content | Blog: 3 seed articles live; 12-week calendar in sheet 05 | Done / ongoing | Doris | One article per week beats twelve in a day.
Content | Add a VideoObject for each episode once trailers/previews are embeddable | Later | Dev | Big opportunity: video rich results for '<story> bible story for kids'.
Local / entity | Google Business Profile not needed (no storefront); focus on Knowledge Panel via Organization schema + Wikidata/Crunchbase entries | Later | Nick

## 04_Schema_Map
Structured data map · Bản đồ schema
Everything is emitted as one JSON-LD @graph per page by build.py.
Page(s) | Types | Key properties | Notes
All pages | Organization (@id #organization), WebSite | name, url, logo, email, sameAs, contactPoint | Rich Results Test → 'Organization' has no rich result but feeds the Knowledge Panel.
/ and /pricing/ | WebApplication + SoftwareApplication with 3 × Offer | applicationCategory, operatingSystem, offers[price, priceCurrency, UnitPriceSpecification], isFamilyFriendly | Software app rich result eligible; keep prices in sync with site.json.
/shows/<slug>/ | TVSeries + BreadcrumbList | name, description, numberOfEpisodes, typicalAgeRange, genre, provider | Add Season / TVEpisode + VideoObject later per episode.
/faq/ | FAQPage + BreadcrumbList | Question / Answer pairs (9) | FAQ rich results are limited to authoritative sites since 2023 — still useful for AI overviews.
/blog/<slug>/ | Article + BreadcrumbList | headline, datePublished, author (Organization), image | Add a Person author later if the team wants bylines.
/about/ | AboutPage + BreadcrumbList | url, name
/contact/ | ContactPage + BreadcrumbList | url, name
/churches/ | BreadcrumbList (consider Service later) | — | If church pricing becomes public, add an Offer with eligibleCustomerType.

## 05_Content_Calendar
12-week content calendar · Lịch nội dung 12 tuần
One post per week, published Monday. Every post links to one show page and the free plan. Repurpose into the Q3/Q4 social calendar.
Week | Publish date | Title (EN) | Góc nội dung (VN) | Target keyword | Internal link | CTA | Repurpose
W1 | 2026-09-14 | Back-to-school mornings: a 10-minute faith routine before the bus | Buổi sáng đi học: routine 10 phút với worship + memory verse | morning routine christian family kids | /shows/worship-and-memory-verses/ | Try free — no card → go.kingdomlandkids.com | Blog post (700–900 words) + 1 IG carousel + 1 Reel hook + Klaviyo note
W2 | 2026-09-21 | How to explain the Exodus to a 6-year-old (without the scary parts) | Giải thích Xuất Hành cho trẻ 6 tuổi | exodus story for kids explained | /shows/bible-adventures/ | Try free — no card → go.kingdomlandkids.com | Blog post (700–900 words) + 1 IG carousel + 1 Reel hook + Klaviyo note
W3 | 2026-09-28 | Screen-time rules that actually work for Christian families | Quy tắc screen time cho gia đình Cơ Đốc | christian family screen time rules | / (why parents choose) | Try free — no card → go.kingdomlandkids.com | Blog post (700–900 words) + 1 IG carousel + 1 Reel hook + Klaviyo note
W4 | 2026-10-05 | Psalm 23 for kids: a bedtime walk-through | Thi Thiên 23 cho trẻ trước giờ ngủ | psalm 23 for kids | /shows/bible-adventures/ | Try free — no card → go.kingdomlandkids.com | Blog post (700–900 words) + 1 IG carousel + 1 Reel hook + Klaviyo note
W5 | 2026-10-12 | What Black History Beats teaches that textbooks skip | Black History Beats dạy gì mà sách giáo khoa bỏ qua | black history for kids christian | /shows/black-history-beats/ | Try free — no card → go.kingdomlandkids.com | Blog post (700–900 words) + 1 IG carousel + 1 Reel hook + Klaviyo note
W6 | 2026-10-19 | A thankful jar: a 4-week Thanksgiving devotional for little kids | Lọ tạ ơn: devotional 4 tuần mùa Thanksgiving | thanksgiving devotional for kids | /blog/five-minute-family-devotional/ | Try free — no card → go.kingdomlandkids.com | Blog post (700–900 words) + 1 IG carousel + 1 Reel hook + Klaviyo note
W7 | 2026-10-26 | Is the annual plan worth it? The honest math for one family | Gói năm có đáng không: phép tính thật | kingdomland kids pricing annual | /pricing/ | Try free — no card → go.kingdomlandkids.com | Blog post (700–900 words) + 1 IG carousel + 1 Reel hook + Klaviyo note
W8 | 2026-11-02 | Advent with a 4-year-old: 24 tiny moments, no crafts required | Mùa Vọng với bé 4 tuổi: 24 khoảnh khắc nhỏ | advent devotional for toddlers | /shows/marvelous-light/ (Christmas) | Try free — no card → go.kingdomlandkids.com | Blog post (700–900 words) + 1 IG carousel + 1 Reel hook + Klaviyo note
W9 | 2026-11-09 | The Christmas story, told by Lucy and Leo (episode guide) | Câu chuyện Giáng Sinh qua Lucy & Leo | christmas bible story cartoon for kids | /shows/marvelous-light/ | Try free — no card → go.kingdomlandkids.com | Blog post (700–900 words) + 1 IG carousel + 1 Reel hook + Klaviyo note
W10 | 2026-11-16 | Gift idea: a year of Bible adventures + a storybook at the door | Ý tưởng quà: gói năm + sách | christian gift for kids subscription | /pricing/ | Try free — no card → go.kingdomlandkids.com | Blog post (700–900 words) + 1 IG carousel + 1 Reel hook + Klaviyo note
W11 | 2026-11-23 | New Year, one verse: picking a family verse for 2027 | Câu Kinh Thánh của gia đình cho 2027 | family bible verse for the year | /shows/worship-and-memory-verses/ | Try free — no card → go.kingdomlandkids.com | Blog post (700–900 words) + 1 IG carousel + 1 Reel hook + Klaviyo note
W12 | 2026-11-30 | Getting ready for MLK Day: songs, stories and one hard question | Chuẩn bị MLK Day: bài hát, câu chuyện, một câu hỏi khó | mlk day activities for kids christian | /shows/black-history-beats/ | Try free — no card → go.kingdomlandkids.com | Blog post (700–900 words) + 1 IG carousel + 1 Reel hook + Klaviyo note

## 06_Links_Distribution
Links & distribution · Backlink và phân phối
Quality over quantity: ten relevant Christian-parenting links beat a thousand directory spam links.
Type | Targets | Play | Priority | Owner
Roundup blogs (Christian moms) | raisingchristiankids.com · equippinggodlywomen.com · mindyjonesblog.com · themillennialsahm.com · proverbialhomemaker.com · crosswalk.com | Pitch 'Kingdomland Kids' for their 'Christian streaming / shows for kids' lists (they already rank; Yippee & Minno are on them). | P0 | Doris
Directories | faith.tools/for-kids · Christian app directories · Common Sense Media listing | Submit listing with logo, screenshots, pricing. | P0 | Doris
Church partners | Every partner church website / newsletter | Ask for a 'Recommended for families' link to /churches/ or the code page. | P1 | Nick
Owned channels | YouTube (159K) channel + video descriptions · IG bio · FB page | Link to kingdomlandkids.com (not only go.), so the root domain accrues authority. | P0 | Jojo / Linh
Creators / ambassadors | Ambassador testimonial creators, 'next Miss Rachel' creator | Ask for a link in bio + post copy pointing to a show page. | P1 | Matt / Nick
Press | Christian parenting podcasts, Black family media, local TX/CA/FL/NY faith outlets | Angle: 'the ad-free Bible app built by and for Black Christian families'. | P2 | Nick
Partnerships | CoinCept (partnership videos already in v1.4), PlayWatchKids sister channel | Cross-link footers and about pages. | P1 | Nick

## 07_Redirect_Map
Redirect map · Bản đồ redirect
Fill the old-URL column from a Screaming Frog crawl of the live site before launch. Every indexed old URL needs a 301.
Old URL | New URL | What it was | Action
https://kingdomlandkids.com/ | / | Home | Keep
(crawl current site) | /shows/ | Any 'shows', 'videos', 'library' page | 301
(crawl current site) | /pricing/ | Any 'plans', 'subscribe', 'pricing' page | 301
(crawl current site) | /about/ | About / our story | 301
(crawl current site) | /faq/ | FAQ / help | 301
(crawl current site) | /contact/ | Contact | 301
go.kingdomlandkids.com/welcome | keep (app) | Paid-ad landing page stays on the app subdomain | No change — but add canonical + noindex if it duplicates /pricing/
Login / account URLs | keep (app) | Header 'Log in' currently points to go.kingdomlandkids.com — replace with the real login URL | Update site.json › urls.login

## 08_Open_Questions
Open questions · Câu hỏi mở trước go-live
Answer these and the site is launch-ready. Each row names the file to edit.
Topic | Question | Where it lands | Ask
Pricing | Q3 plan says $9.99/mo ($7.99 first month) + $69.99/yr. Slack (Jun 14) says the live site is $7.99/mo + $69.99/yr. Which is live today? | site.json › pricing | Nick
Ages | Site says 'ages 2–10' overall, 4–8 for most shows. OK to publish? | site.json › description, hero kicker, FAQ | Doris
Devices | Copy says 'browser on phone/tablet/laptop + TV via casting'. Are there native apps (iOS/Android/Roku/Fire TV)? If yes we add store badges + SoftwareApplication per platform. | Home devices section, FAQ | Khai
Login URL | Real login URL for the header button (currently go.kingdomlandkids.com). | site.json › urls.login | Khai
Social URLs | Confirm Instagram and Facebook handles (YouTube confirmed). | site.json › urls | Jojo
Testimonials | Two quotes carried over from the current site — attribution / permission to keep using them? | site.json › testimonials | Nick
Series facts | Bible Adventures '15 episodes', Little Agent '8 missions', ABCs & Numbers count, Bible in Clay status (new? live?), Grandpa Moses series — confirm counts and names. | site.json › series | Matt
Storybook | Annual bonus ships to U.S. addresses only? Any timeline? | Pricing page note, FAQ | Nick
Church rate | Is the church promo price public (e.g., $4.99/mo)? If yes we show it on /churches/. | churches page | Nick
Logo & key art | Need: Kingdomland wordmark SVG, series thumbnails (16:10), character art (Lucy, Leo, RJ, Rylee), app screenshots for the device mockups. | header/footer, show cards, devices | Doris
Legal | Privacy Policy + Terms text (currently placeholders, noindex). | /privacy/, /terms/ | Nick
Hosting | Where does the new site deploy (Netlify/Vercel/Cloudflare)? Who owns DNS for kingdomlandkids.com? | — | Khai
Old URLs | Export of current site URLs (or Screaming Frog crawl) for the redirect map. | 07_Redirect_Map | Khai